Pager Meeting March 17

# (1) Status Quo

## Tasks completed since last Meeting

* Finding relevant literature and get an overview of topic
* Research, Note-Taking, Structuring and Writing Process started

## Changes & Challenges

* Extended Framework phase from 3 to 4 Weeks
* Decided to write Exploration Chapter only if enough pages left

## Personal reflection

* **Past**: Having ups and downs - Note taking and Research felt very efficient, but needed time to get into the writing process (better now).
* **Future Objectives**: Goals of completing Framework by end of next weeks seems doable. It is however hard to estimate the speed of writing.
* **Challenge**: Need to be careful to define scope of methodology not to overburden myself. Better to do less tasks very well, than a bunch of tasks mediocre
* **Topic**: Surprisingly interested in the topic, had a pleasure reading fowler’s work.

# (2) Open Questions

* **Tests:** Discuss the importance of writing tests.
* **Methodology:** How much can be written before implementation?
* **Citation:** Reference Author or Author + Page Number?

# (3) Outlook

### First Week: Writing

* Finish writing theoretical framework (approx. 10 - 15 Pages)
* Communicate to Ronny when is able to start reading the draft

### Second Week: Refactoring work

* Write Methodology the parts that are already possible (5 - 10 Pages)
* Formulate Hypotheses
* Broad Analysis (with Tools)

## Next Meeting

Proposed Date: 31. March (in 2 weeks)

* Getting a Feedback on first draft (theory)
* Discuss upcoming Challenges / Questions regarding the refactor